## V1
Project Development and Completion Tracker
Porject ID: 1.0
Project Start Date: 16-03-2024 Project End Date: 29-04-2024
Porject Descreption: Keylogger software for software companies
| Name of Team member | Designation |  | Name of Students |  | Role |  | Name | Designation
Project Architech Team Members | Hemanshu Moundekar | Group Leader | Project Development Student Team Memebers | Hemanshu Moundekar |  | Team Lead | Project Domain Expert Team Members (Geolife)
| Durgesh Borse |  |  | Durgesh Borse | Sourabh Karmakar | Frond End
| Sourabh Karmakar |  |  |  |  | Team Lead
Front/Back End
Team Lead
Back End
Front End
Epic: | As an employer/parent I should know what my employee/ward is doing.
Story 1: | I don’t know what is my child’s activity on internet.
Story 2: | I don’t know what my employee’s does on company’s device.
Task1: | Define how will keylogger work
Task2: | Try out different types of libraries
Task3: | Find out Reasearch Paper on Keylogger
Acceptance Criteria:
1 | Should include the proper working of Keylogger and its procedure
2 | The libraries will help in finding out which library will be good to be used
3 | With Reasearch paper we can check for references and gain more knowledge.
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 0 | Find More information on Keylogger | Types of Keylogger | Complete | Durgesh, Sourabh | 2024-03-01 | 01-03-2024 | 01-03-2024 | 14-03-2024 | 100% | Not Started | Medium
|  | keylogger Process | Complete | Anjali, Shruti | 2024-03-01 | 01-03-2024 | 2024-03-01 | 14-03-2024 | 100%
| Reasech Paper Hunt | Finding Reasearch Paper | Complete | All | 2024-03-20 | 10-04-2024 | 2024-03-22 | 04-04-2024 | 100%
Sprint 1 | Find out Libraries for Keylogger | Finding libraries for Keylogger | Complete | Hemanshu | 2024-03-15 | 03-04-2024 | 2024-03-15 | 06-04-2024 | 100% | On Hold
| Write code for Keylogger using the library | Writing code, and Learning | Complete | Hemanshu | 2024-04-07 | 28-04-2024 | 2024-04-07 | 28-04-2024 | 10% | Overdue
| Testing and Debugging of keylogger | Testing and Debugging Of Keylogger | In Progress | All | 2024-04-28 | 30-04-2024 | 2024-04-28 | 30-04-2024 | 80%

## Version 2
Project Development and Completion Tracker
Porject ID: Version 2
Project Start Date: 15-03-2021 Project End Date:
Porject Descreption: Android and ios application for farmers to monitor growth of crop, fertilizer recomendation and providing regionwise market analysis of crop. (V1) Along with crop growth calendar and stagewise NPK requirement calculation.
| Name of Team member | Designation |  | Name of Students |  | Role |  | Name | Designation
Project Architech Team Members |  |  | Project Development Student Team Memebers |  |  | Team Lead | Project Domain Expert Team Members (Geolife)
Frond End
Team Lead
Front/Back End
Team Lead
Back End
Front End
Epic: | As a farmer, I should know fertilizer requirement for my crop in my region to fulfill N,P,K.
Story 1: | As a farmer, I should get growth calendar of crop.
Story 2: | As a farmer, I should know growth wise activity reminder of crop.
Story 3: | As a farmer, need stagewise reccomendation of fertilizer to fulfil N,P,K requiremnt of my crop.
Task1: | Design a layout to select crop.
Task2: | Design a layout to select sowing date for crop.
Task3: | Design a layout which will display crop calendar contaiinng stages like watering, pestisides, fertilizer, etc.
Task4: | Create reminders in calendar along with details of each stage with its all possible recommendation.
Task5: | Incorporate NPK requirement to growth calendar stagewise by considering soil contribution and efficacy of crop.
Acceptance Criteria:
1 | Farmer can select crop for sowing in the season out of list with images.
2 | Farmer can select date of sowing with validation.
3 | Completion of stages of crop in calendar are visibille and reminders get pop-up.
4 | When task get completed by farmer, he can input completion of task.
5 | Farmer can view NPK stages requirement and add completion status.
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 1 | Design a layout to select crop. | Creating layout of showing crop categories | Complete | Sunny Yadav, Sumeet Sapkal |  | 25-10-2021 |  |  | 100% | Not Started | Medium
|  | After selecting category, show crop images and selection. | Complete | Sunny Yadav, Sumeet Sapkal |  | 25-10-2021 |  |  | 100%
| Design a layout to select sowing date for crop. | Use calendar API in app. | Complete | Siddhant Oswal, Simon Singh |  | 25-10-2021 |  |  | 100% | In Progress | Low
|  | Show sowing date selction in app. | Complete | Simon Singh, Siddhant Oswal |  | 25-10-2021 |  |  | 100%
| Design a layout which will display crop calendar containg stages like watering, pestisides, fertilizer, etc. | Create database of all crops containg growth stages, watering, pestiside and fertilizer dates. | In Progress | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 50% | Complete | High
|  | Create reminders and display details and recomendation of each stage. | Not Started | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0%
| When task get completed by farmer, he can input completion of task. | Activity will be in active state till completion. User will make it completed by input. | Not Started | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0%
|  | User inputs get reflected in database as well. | On Hold | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0% | On Hold
| Farmer can view NPK stages requirement and add completion status. | NPK requirement calculation as per growth stage. | Complete | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 100% | Overdue
|  | Include these data in calendar. | In Progress | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 20%

## Student Team
STUDENT INTERN LIST
Sr. No. | Name of Inern | Email Address | Contact | class | Domain (Web, App, Backend)
1 | Prajwal Sah | prajwalsah212@gmail.com | 7776012981 | FY IT DA | ML
2 | Shriya Dilliwale | anitashriya12@gmail.com | 7559361354 | FY IT DA | Flutter, ML | Version 1
3 | Nikhil Chavan | nikhilchavan407@gmail.com | 8369686747 | FY IT - CORE | Flutter | Version 1
4 | Vipul Kumar Singh | vipulkumarbhore@gmail.com | 7764059016 | FY IT - CORE | Flutter | Version 2
5
6
8
9
10
3 | Anjali Bhatt | anjalibhatt601@gmail.com | 830811254 | FY CSE Core 2 | Flutter, ML | Version 1
4 | Shruti Singasane | singasane.shruti2001@gmail.com | 8652233102 | FY CSE Core 2 | Flutter, ML | Version 1
5 | Rushil Jain | rushiljain2001@gmail.com | 9371775841 | FY CSE IS 1 | Flutter, ML | Version 1
7 | Sumeet Sapkal | sumeetspkl@gmail.com | 9112156784 | FY CSE | Flutter, MySQL | Version 2
8 | Sunny Yadav | sunnyyadavtheone@gmail.com | 7878964402 | FY CSE | Flutter, MySQL | Version 2
9 | Siddhant Oswal | oswalsiddhant2001@gmail.com | 8329979013 | FY CSE | Flutter | Version 2
10 | Simon Singh | simonsinghdomain@gmail.com | 7470659108 | FY CSE | Flutter | Version 2
11 | Varun Kapse | varunkapse07@gmail.com | 8830624385 | FY IT - PASSED | ML | Version 2
13 | Rutvi Nair | rutvinar305098@gmail.com | 8141393918 | TY CSE IS 1 | Flutter | Version 2